## Measurement
Item Code | Description | Date | Measurement For | Number | Typical Formula | Length | Breadth | Height | Rate | Quantity | Amount | uom | Pending Quantity | Executed Quantity
2 | Earth work open excavation in all soils and sub-soils and to full depth as may be directed except in rock requiring blasting inclusive of shoring shuttering | 13/Apr/2026 | [6 empty] | 103.83 |  |  | cum | 87 | 3
3 | Supplying and filling in foundation, basement, etc with filling crushed stone sand in layers of not more than 15 cm thick well watered, rammed and consolidated etc. complete complying with standard specification and as directed by the departmental officers. | 13/Apr/2026 | [6 empty] | 1689.07 |  |  | cum | 28 | 2
4 | Supplying and filling 40mm guauge HBGS stone jelly for dispersion trench including loading conveying and unloading and as directed by the departmental officers etc. complete complying with standard specification. | 13/Apr/2026 | [6 empty] | 1396.4 |  |  | cum | 23 | 7
5 | Supplying and filling 20mm guauge HBGS stone jelly for dispersion trench including loading conveying and unloading and as directed by the departmental officers etc. complete complying with standard specification. | 13/Apr/2026 | [6 empty] | 1849.4 |  |  | cum | 30 | 0
6 | Supplying and erecting centering for plane surfaces such as RCC Floor Slab, Roof Slab, Loft, Landing Slabs, etc with necessary supports and strutting upto 3.60m height in all floors with all cross bracings using MS Sheets made of 10 gauge thick welded with MS angle of Size 25mm x 25mm x 3mm for boarding laid over steel adjustable span of size | 13/Apr/2026 | [6 empty] | 889.27 |  |  | cum | 7.1 | 0
7a | Providing and laying in position, standardised concrete Mix M-20 Grade by insitu machine mix concrete adopting weighing batch method in accordance with IS 456 using 20mm and down graded hard broken granite stone jelly for all RCC items of works with minimum cement content of 325 kg/m3 and maximum water cement ratio of 0.55, including admixture (plasticiser / super plasticiser) in recommended proportions as per IS:9103 to accelerate, retard setting of concrete, improve workability without impairing strength and durability with about (5 cu.m.) 7730 kg. of 20mm machine crushed stone jelly and with about (3.3 cu.m.) 5156 kg. of 10-12mm machine crushed stone jelly and with about (4.79 cu.m) 7670 kg. of crushed stone sand, but excluding cost of reinforcement grill and fabricating charges, centering and shuttering and also including laying, vibrating with mechanical vibrators, finishing, curing, etc. and providing fixtures like fan clamps in the RCC floor/ roof slabs wherever necessary without claiming extra, etc., complete complying with standard specification and as directed by the departmental officers. The coarse and fine aggregates to be used should comply with the requirements of IS standards. (No separate payment will be made by the Department for the excess usage of materials).-For S.S. in Ground floor | 13/Apr/2026 | [6 empty] | 8049.13 |  |  | cum | 1 | 0
9 | Finishing the top of roof with one course of machine pressed tiles of size 230x230x16mm to 18mm approved quality set in Cement Mortar 1:3 (One Cement and Three Crushed stone Sand) 12mm thick mixed with water proofing compound conforming to ISS at 2% by weight of cement used and the joints pointed neatly to full depth of tiles with the same cement mortar mixed with red oxide and water proofing compound including curing etc., complete complying with standard specification and as directed by the departmental officers | 13/Apr/2026 | [6 empty] | 1286.9 |  |  | sqm | 254 | 0
10 | Pointing the top of roof with one course of machine pressed tiles of following size of approved quality set in Cement Mortar 1:3 (One Cement and Three Crushed stone Sand) 12mm thick mixed with water proofing compound conforming to ISS at 2% by weight of cement used and the joints pointed neatly to full depth of tiles with the same cement mortar mixed with red oxide and water proofing compound including curing etc., complete complying with standard specification and as directed by the departmental officers | 13/Apr/2026 | [6 empty] | 347.69 |  |  | sqm | 545 | 160
11 | Paving the floor with best approved quality fine polished Kota stone slabs | 13/Apr/2026 | [6 empty] | 1406.02 |  |  | sqm | 41 | 0
12 | Supply and fixing doors as per drawings with WPC solid 3layer and ISI marked flush door shutters of 35 mm thick single shutter with | 13/Apr/2026 | [6 empty] | 7400 |  |  | sqm | 47.5 | 0
13 | SUPPLYING AND FIXING COST OF WIND APPLIANCES AND FURNITURE FITTINGS SUCH AS 1NO .300 X 12 MM ALUMINIUM TOWER BOLT 2 NOS. 200X12 MM ALUMINIUM TOWER BOLTS 1NO. 250 X 16 MM ALUMINIUM A | 13/Apr/2026 | [6 empty] | 786.45 |  |  | sqm | 117 | 17
14 | Supplying and fixing of Plain Glass of 5.50 mm thick and including cost of labour and materials etc., | 13/Apr/2026 | [6 empty] | 628 |  |  | sqm | 192 | 7
15 | Supplying and Fixing of MS Netlon Screen with Aluminium anodised Powder Coated outer frame of size 2" x 1" with magnetic catch arrangements having stainless steel handle and including cost of necessary accessories, materials, labour charges and power consumption charges etc., complete complying with standard specifications. | 13/Apr/2026 | [6 empty] | 4250 |  |  | sqm | 90.5 | 2
16 | Special ceiling plastering and finishing the exposed surface of all RCC items of work such as slabs, beams, sunshades, facia, canopy slab, staircase waist slab, landing slab etc., with Cement Mortar 1:3 (One Cement and Three Plastering Sand) 10mm thick including mortar plasticizer at 200ml per 50Kg of cement used , hacking the surfaces and curing, etc., in all floors complying with standard specification and as directed by the departmental officers | 13/Apr/2026 | [6 empty] | 315.75 |  |  | sqm | 659 | 0
17 | Distempering the old wall and ceiling one coat with best oil bound distember of approved quality including preparation of surface, the rate includes cost of brushes, high scaffolding arrangements, neat finishes, etc., complete complying with standard specification and as directed by the departmental officers. | 13/Apr/2026 | [6 empty] | 68.75 |  |  | sqm | 6379 | 0
18 | Painting the old wall two coats with approved weather proof Exterior Emulsion paint over on cement plastered wall surface ect., complete complying with standard specification and as directed by the departmental officers. | 13/Apr/2026 | [6 empty] | 174.96 |  |  | sqm | 2793 | 0
19 | Providing two legged scaffolding using 15cm diameter blue-gum posts or casuarina posts or best quality bamboo posts of 4m over all length (3m+0.5m projection+0.5m into the ground) the distance between the two rows being 1.25m and the spacing of posts being 2m in both the rows with two horizontal posts with 0.5m overlap on either side and braces at2m c/c including longitudinal and transverse middle braces to step up and providing a platform with country wood planks of 40mm thick and 1m width etc.,in a complete form using coir and nails 1m run. | 13/Apr/2026 | [6 empty] | 1436.9 |  |  | Rm | 289 | 0
20 | Painting Old wood work with Two coat of synthetic enamel ready mixed paint of approved quality and colour in all floors etc., complete complying with standard specification and as directed by the departmental officers. (The make, quality and colour of paint should be got approved by the Executive Engineer before use on works.) | 13/Apr/2026 | [6 empty] | 160.27 |  |  | sqm | 411 | 0
21 | Painting Old iron works such as steel doors, windows, ventilators, window bars, balustrades etc., with Two coats of best approved first quality and colour of synthetic enamel paint in all floors etc., complete complying with standard specification and as directed by the departmental officers.(The make, quality and colour of paint should be got approved by the Executive Engineer before use on works.) | 13/Apr/2026 | [6 empty] | 141.28 |  |  | sqm | 327 | 0
22 | Supplying and fixing in positon Indian Water Closet (Oriya type) of size 580 x 440mm white glazed earthern ware of approved quality and brand with "P" or "S" trap conforming to BIS with crushed stone sand cushion and forming flooring alround the closet using 40mm broken brick jelly in lime concrete 1:2:5 (One lime, Two crushed stone sandand Five brick jelly) 100mm thick and finishing the top to the required slope and including giving necessary connection to CI soil pipes (including the cost of 100mm dia CI pipe for a length of 600mm) by dismantling brick masonry wall / reinforced cement concrete roof / floor slab and making good the dismantled portion to the original condition with leakages etc., complete complying with standard specifications and as directed by the departmental officers. (The water closet should be got approved by the Executive Engineer before use on works). | 13/Apr/2026 | [6 empty] | 5863.8 |  |  | each | 9 | 0
23 | Supplying and fixing in position white glazed European Water Closet of best quality and approved make with 100 mm "P" or "S" trap connecting with PVC pipe of 110mm dia, double flapped rigid PVC black seat and seat cover with CP brass hinges including cost of white cement, cement for packing, spun yarn, teak wood plugs, brass screws, etc., including supplying and fixing 10 litres capacity PVC | 13/Apr/2026 | [6 empty] | 6441.3 |  |  | each | 6 | 0
24 | Supplying and fixing in position 15mm dia brass CP screw down tap (heavy duty) of approved make conforming to BIS specifications and quality including cost of shellac, thread, etc., complete complying with standard specification and including cutting and threading wherever necessary. (Taps should be got approved by the Executive Engineer before use on the works) | 13/Apr/2026 | [6 empty] | 379.31 |  |  | each | 75 | 0
25 | Supplying and fixing approved best quality brass CP towel rail 600mm long and 20mm dia with brackets of same materials including cost of teak wood plugs and CP screws, etc., complete complying with standard specifications. (The tower rail should be got approved by Executive Engineer before use on works). | 13/Apr/2026 | [6 empty] | 545.55 |  |  | each | 27 | 0
26 | Supplying and fixing in position Indian make bevelled edge mirror of approved quality and brand PVC / Fibre Glass framed 5.5mm thick mirror of Size :600 x 450 mm, Shelf type with hard board backing of approved colour fixed with brass screws, rawl plug, etc., complete complying with standard specification. (The mirror should be got approved by the Executive Engineer before use on woks) | 13/Apr/2026 | [6 empty] | 1116 |  |  | each | 27 | 0
27 | Supplying and fixing in position best approved of BIS quality 110mm dia PVC rain water down fall pipes having a pressure of 4 kg. / sq.cm including cost of necessry PVC shoe, PVC bend, cast iron gratings of required diameter and special clamps, brass screws, nails, etc., and fixing of cast iron gratings at junction of parapet and the RCC roof slab including finishing neatly etc., complete. The rate shall be inclusive of cast of removable cast iron grating. The PVC pipe shall be fixed in wall with special type of "U" clamp at the centre of the pipe line in addition to those for more than 3.0 metre pipe length, etc., complete complying with standard specification and as directed by the departmental officers | 13/Apr/2026 | [6 empty] | 620.67 |  |  | Rm | 291.2 | 0
28a | 50mm dia | 13/Apr/2026 | [6 empty] | 558.4 |  |  | Rm | 90 | 0
28b | 40mm dia | 13/Apr/2026 | [6 empty] | 418.45 |  |  | Rm | 90 | 0
29a | UPVC pipes 32mm dia | 13/Apr/2026 | [6 empty] | 356.35 |  |  | Rm | 90 | 0
29b | 25mm dia | 13/Apr/2026 | [6 empty] | 254.7 |  |  | Rm | 121.5 | 0
30a | 50mm dia Elbow | 13/Apr/2026 | [6 empty] | 87.8 |  |  | each | 10 | 0
30b | 40mm dia Elbow | 13/Apr/2026 | [6 empty] | 58.4 |  |  | each | 10 | 0
30c | 32mm dia Elbow | 13/Apr/2026 | [6 empty] | 43.8 |  |  | each | 20 | 0
30d | 25mm dia Elbow | 13/Apr/2026 | [6 empty] | 29.1 |  |  | each | 20 | 0
30e | 50mm dia Tee | 13/Apr/2026 | [6 empty] | 121.8 |  |  | each | 15 | 0
30f | 40mm dia Tee | 13/Apr/2026 | [6 empty] | 75.6 |  |  | each | 15 | 0
30g | 32mm dia Tee | 13/Apr/2026 | [6 empty] | 57 |  |  | each | 15 | 0
30h | 25mm dia Tee | 13/Apr/2026 | [6 empty] | 38.5 |  |  | each | 10 | 0
30i | 50mm dia Bend | 13/Apr/2026 | [6 empty] | 82.3 |  |  | each | 10 | 0
30j | 40mm dia Bend | 13/Apr/2026 | [6 empty] | 58.8 |  |  | each | 10 | 0
30k | 32mm dia Bend | 13/Apr/2026 | [6 empty] | 41.1 |  |  | each | 10 | 0
30l | 25mm dia Bend | 13/Apr/2026 | [6 empty] | 32.8 |  |  | each | 15 | 0
30m | 32mm x 25mm dia Reducer | 13/Apr/2026 | [6 empty] | 27.9 |  |  | each | 10 | 0
30n | 32mm x 40mm dia Reducer | 13/Apr/2026 | [6 empty] | 38.5 |  |  | each | 15 | 0
30o | 40mm x 50mm dia Reducer | 13/Apr/2026 | [6 empty] | 60 |  |  | each | 8 | 0
31 | Supplying, laying and jointing 25mm dia CPVC pipes OF Standard Dimension Ratio 11 (Pressure class 1) conforming to IS:15778 - 2007 of approved quality and best variety of the following dia including cutting and fixing CPVC specials using CPVC adhesives (Solvent Cement) (but excluding cost of such specials) and fixing into wall with teak wood plugs, CPVC clamps and screws making holes on the wall (or) drilling holes in the roof and making good the dismantled portion to original condition with necessary brick work / cement concrete and plastering neatly wherever necessary with necessary scaffolding charges, etc., complete complying with standard specifications and as directed by the departmental officers. (The CPVC pipes shall be got approved by Executive Engineer before use on works) - Internal water supply above ground level. | 13/Apr/2026 | [6 empty] | 334.1 |  |  | Rm | 72 | 0
32a | 25mm dia Elbow | 13/Apr/2026 | [6 empty] | 50.5 |  |  | Rm | 15 | 0
32b | 25mm dia Tee | 13/Apr/2026 | [6 empty] | 60.9 |  |  | Rm | 15 | 0
32c | 25mm dia Bend | 13/Apr/2026 | [6 empty] | 47 |  |  | Rm | 15 | 0
33a | 110 mm dia | 13/Apr/2026 | [6 empty] | 506.8 |  |  | Rm | 268.8 | 0
33b | 75 mm dia | 13/Apr/2026 | [6 empty] | 396.3 |  |  | Rm | 268.8 | 0
34a | 110 mm Elbow | 13/Apr/2026 | [6 empty] | 442.85 |  |  | each | 7 | 0
34b | 110 mm Elbow door | 13/Apr/2026 | [6 empty] | 509.6 |  |  | each | 5 | 0
35a | 25 mm dia | 13/Apr/2026 | [6 empty] | 1022.1 |  |  | each | 5 | 0
35b | 32 mm dia | 13/Apr/2026 | [6 empty] | 1329.5 |  |  | each | 5 | 0
35c | 40 mm dia | 13/Apr/2026 | [6 empty] | 1548.65 |  |  | each | 5 | 0
35d | 50 mm dia | 13/Apr/2026 | [6 empty] | 2105 |  |  | each | 5 | 0
36 | Supplying and fixing of The Semi-Automatic Roti (Chapati) Making Machine , stainless steel unit designed for efficient and consistent chapati production. Manufactured in India, this machine features a robust 1 HP electric motor with a speed of 1440 RPM, operating on a single-phase power supply. It supports a chapati size range of 3 to 9 inches (76.2 mm to 228.6 mm) with a compact overall size of 12.192 cm, making it ideal for both small and large-scale food production environments. With a production capacity of 850 to 950 chapatis per hour, this machine ensures fast output without compromising quality.The silver-finished stainless steel construction ensures durability, hygiene, and ease of maintenance. | 13/Apr/2026 | [6 empty] | 93450 |  |  | each | 1 | 0
37 | SUPPLYING AND FIXING OF HARD TOP DEEP FREEZER IS A HIGH-CAPACITY, CONVERTIBLE COOLING APPLIANCE DESIGNED FOR EFFICIENT COMMERCIAL USE. WITH A TOTAL CAPACITY OF 563 LITERS, IT FALLS INTO THE 500 L & ABOVE CATEGORY, MAKING IT IDEAL FOR STORAGE-HEAVY ENVIRONMENTS SUCH AS SUPERMARKETS, RESTAURANTS, AND COLD STORAGE FACILITIES. THIS STANDALONE, DOUBLE-DOOR FREEZER FEATURES A HARD TOP DESIGN AND IS BUILT WITH COMPRESSOR-BASED COOLING TECHNOLOGY, OFFERING A TEMPERATURE RANGE | 13/Apr/2026 | [6 empty] | 47125 |  |  | each | 1 | 0
38 | WORK BENCH | 13/Apr/2026 | [6 empty] | 17500 |  |  | each | 1 | 0
39 | SS STORAGE RACK: 4 TIER SIZE 44 | 13/Apr/2026 | [6 empty] | 27500 |  |  | each | 1 | 0
40 | SUPPLYING AND FIXING OF A HIGH-QUALITY 32-LITER BAIN MARIE DESIGNED FOR EFFICIENT FOOD WARMING AND SERVING IN COMMERCIAL KITCHENS, BUFFETS, AND CATERING ENVIRONMENTS. CONSTRUCTED WITH HEAVY GAUGE STAINLESS STEEL, THE UNIT FEATURES A DURABLE STAINLESS STEEL OUTER BODY AND INCL | 13/Apr/2026 | [6 empty] | 34000 |  |  | each | 1 | 0
41 | Supplying and commissionoing of Industrial Heavy Mixi motor with cocount scrapper 2 - litre with electrical arrangement including cost of all materials, Conveyance and labour etc., | 13/Apr/2026 | [6 empty] | 26500 |  |  | each | 2 | 0
42 | Supplying and fixing the Idly Cooking Plant 240 Nos Cap and it is fabricated by 304 grade SS Sheet. The outer chamber and idly trays, are made of 1.25 mm thick and the inner chamber of 1.6 mm thick. It is fitted with all accessories viz., Automatic steam control system. this equipments has two independent chambers. Each chamber contains five numbers of idly trays with idly stand. One tray contains 20 numbers of iddlies the rate including cost of ss less. The rate including cost of all materials, Conveyance and labour etc., | 13/Apr/2026 | [6 empty] | 52000 |  |  | each | 1 | 0
43 | GAS PIPE LINE FITTINGS. HAVING CYLINDERS (5+5) MANIFOLDING SYSTEM WITH D.B.C. CLICKING ON H.P.REGULATOR,REGULATOR CONNECTOR, SHUT OFF VALVES,UNIT VALVES,WITH FRAME CONNECTOR AND T | 13/Apr/2026 | [6 empty] | 180000 |  |  | each | 1 | 0
44 | Supplying and fixing of 8 seater Dinning table (full ss) attached with seat of table top frame 32 mm SS 304 Grade square tube and top by 1.25 mm SS 304 Grade Sheet packed with 6 mm plywood for reinforcement. Legs are 40 mm SS 304 Grade round pipe and cross pipe 32 mm round pipe with fixed shetter. Shetter by SS readymade plate of size 96" x 36" x 30" the rates are inclusives of loading, unloading, transportaions, etc., Complete complying with standard spefications., (2.40x0.90x0.75m) | 13/Apr/2026 | [6 empty] | 78408 |  |  | each | 2 | 0
45 | Supplying and fixing Vegetable cutter 1 HP Mini Vegetable Cutting Machine. This powerhouse of a device comes equipped with 8 versatile blades, making it a must-have for any commercial kitchen. It effortlessly handles a wide range of vegetables, reducing preparation time and ensuring uniform cuts. With a robust 1 HP motor, it's built for durability and efficiency. Trust in Confider Industries to deliver top-notch kitchen solutions, simplifying your kitchen food preparation needs. | 13/Apr/2026 | [6 empty] | 27750 |  |  | each | 1 | 0
46 | Supplying and commissioning of Milk Boiling, Vessel the inner vessel is fabricated by 304 grade 2B finish 2 mm thickness stainless steel sheet. The inner bottom dished portion is kept at a distance of 100 mm bottom plate for the effective functioning. | 13/Apr/2026 | [6 empty] | 40000 |  |  | each | 1 | 0
47 | THE INDUSTRIAL WASHER EXTRACTOR AND DRYER YOU'RE LOOKING FOR SEEMS TO BE A HIGH-CAPACITY MACHINE DESIGNED FOR HEAVY-DUTY LAUNDRY APPLICATIONS. HERE'S A BREAKDOWN OF THE SPECIFICATIONS BASED ON SIMIL | 13/Apr/2026 | [6 empty] | 135000 |  |  | each | 1 | 0
48 | SUPPLYING AND ERECTING IN POSITION OF 50 LITERS STORAGE CAPACITY WITH HOT, COLD AND NORMAL WATER DISPENSER AND REVERSE OSMOSIS WATER-CUM- PURIFIER TO DELIVER POTABLE WATER WITH WORLD HEALTH ORGANISATION (WHO) STANDARDS WITH FOLLOWING ACCESSORIES. (A) MS SKID - 1 NO. (B) MEDIA 11054 NO. VESSEL WITH 20 NB MULTIPORT VALVE (WITH MEDIA PUBBLE AND FINE SAND AND ACTIVATED CARBON FILLING) S | 13/Apr/2026 | [6 empty] | 85000 |  |  | each | 3 | 0
49 | Supplying and fixing of GYM equpiments inclludings Dumbells, Bench Press, Wall mounted bar, Helipitical Machine, Cycling Equpiments, Kettles, etc complete stanadard specifiactions | 13/Apr/2026 | [6 empty] | 127000 |  |  | Set | 1 | 0
50 | Finishing the Existing spalled concrete portion to chip the deboned cover of concrete to expose the damaged reinforcement to remove the correction by applying rust removing liquid to clean the rust released reinforcement 'NITO ZINC PRIMER' mxing 1 part SBR : 1 part of cement to apply a tacky bond coat of NITO BOND SBR LATEX' mixing at the rate of 1 part of SBR : 1 part Of water :4 part of cement over entire chip off surface which is to receive subsequent micro concrete 'RENDEROC RG' to 25mm to 40mm to finish the surface smooth using trowel cost includes cement sand all chemicals application labour tools and tackles transportation of material in etc., complete | 13/Apr/2026 | [6 empty] | 920 |  |  | sqm | 190 | 0

## Units
cum
each
quintal
Rm
Set
sqm

## Typical Formula
l * w
a * a
(b * h) / 2
pi * r * r
((b1 + b2) * h) / 2
b * h
pi * a * b
al / (e * t * l)
((a1 + a2) / 2) * l
(rise / run) * 100
l * a * s
a * s
p / a
((a+b)/2)
((a+b+c)/3)
(n * (h / 3) * ((b1 * b2) + (t1 * t2) + (b1 * b2 * t1 * t2)^(1/2)))
(n * l * ((pi / 4) * (d^2) * (7850 / 10^6)))